CONFERENCE CHAIR

TIME LINE

(October 2019)

TEDA Conference Chair

Time Line

Year round responsibilities

- Monitor and respond to conference email daily, more when closer to the conference

- Send all flyers, announcements, matrix etc. to the past president for editing and approval prior to use and distribution

- Prepare conference reports for board meetings

At conference the year prior and for upcoming (the next year)

- Prepare and distribute a save the date announcing conference location and date

10-12 months prior to conference:

- Based on previous year’s budget, prepare a proposed budget for board approval and send appropriate officer (treasurer?)

- Book keynote speakers

- Confirm conference center and hotel contracts with each

- Determine theme and use for flyer graphics

- Prepare and send to post initial flyer on line and send for distribution through email and DiaLog

- Prepare registration form

- Have conference tab from previous year cleared

- Have committee decide how it will do the reception, if they will do a reception and what the needs for that are

  - When and where

  - Food or no food

  - Activity or not (Back to basics: diag 101, poster session, round table…) are presenters needed, who and what will that look like

6-8 months prior to conference

- Send registration form for distribution and for posting

- Book breakout speakers

- Once speakers are confirmed, prepare new flyer with all speakers on it

- At about 6 months prior depending on when the conference is and when DiaLog will be published, send new flyer and registration form for distribution

- Send flyer with deaf ed strand information to a lead for deaf ed at your esc and ask her/him to send to all deaf ed coops with a brief note pointing out the deaf ed strand

3-6 months prior

- Complete all speaker contracts (best done as soon as speakers confirm)

- Generate a list of speaker needs based on contract information

  - Hotel rooms

  - AV

  - Food

  - handouts

  - Anything else they mention

Conference Chair						1				October 2019

- Prepare hotel rooming list of board members and speakers, send to hotel when complete (about 3 months out)

- Research books/gifts for TEDA members who attend the conference, number ordered will change based on registration, so wait as long as the publisher will allow to order to have a better idea how many members will attend (include board and pad a little for onsite registration

- Check with Jeanne and possibly Houmet to see if they will be providing gifts for the conference, Jeanne’s chapter usually does the notepads, consider a pen with those

- Prepare matrix (written schedule) and send to website for posting

  - Location

  - Speakers

  - Dates and times each session/activity begins and ends

  - Rooms for each speaker

- Keep updated as to registration numbers

- Determine what the menu will be for the luncheon and what the conference will do for lunch the second day (speakers and board get lunch provided)

- Confirm with vendor chair the number of vendors and tables needed, provide this information to conference center

- Begin monitoring hotel occupancy and determine if overflow room are needed, continue to monitor

- Confirm that a new W-9 has been completed by treasurer and is available through the TEDA administrative assistant for districts who request it. Many districts will need a current one with the correct year on it, you usually cannot reuse the same one for some districts.

3-4 weeks prior

- Collect handouts from speakers who said they would send electronically and send for posting under password protected tab

- Finalize menu with conference center, but not numbers

- Send AV needs to conference center, list by room not speaker, include a matrix for conference center use

- Confirm vendor set up with vendor chair then with conference center

- If books have not been ordered they need to be ordered now

- Choose the method you will prepare the gift for handout and purchase the materials needed to do so (check with Jeanne)

- Confirm what chapters will donate to be included with gift (usually Jeanne’s chapter, but ask Houmet)

- Confirm whether or not door prizes will be used and how

- Purchase name badge holders (over buy, they can be used the next year and registration will not be complete at this time)

- Continue to monitor registration numbers and hotel occupancy for any needs

- Have posted the last date for registration, both on line and hard copy, stating any registrations after that date will be on site.  Need to include note that on site registrations do not include a guarantee of luncheon or members gift.  You need a count 1 week prior for food, and need to prepare paperwork, suggest closing one week prior.

- Update budget with expenses to date and income

Conference Chair						2				October 2019

1-2 weeks prior to conference

- Confirm the date of and then close of on line registration (all others will be on site) you need a count 1 week prior for food, and need to prepare paperwork, suggest closing one week out

- Confirm the number of registered attendees

- Confirm number of TEDA members registered

- Generate general assembly/luncheon numbers and use for conference center meal confirmation

  - All registered TEDA members

  - Board

  - Speakers who chose to have lunch on their contracts

- Have TEDA administrative assistant send you the following lists for registration

  - List 1: Sign in sheet, all registered attendees by last name (include full name, with indication whether or not they are a TEDA member, district and signature line)

  - List 2: all registered attendees by district (include full name and district)

  - On-site registration sign in (include column for name, district and signature line)

- Prepare conference materials

  - Confirm that administrative assistant will print 2 copies of list 1, 2 copies of list 2 and one on-site registration list or have them printed yourself with the other materials

  - Receipt book

  - Signs for registration (letters of the alphabet for lines determined by number of registrations in each)

  - Check with Jeanne about table decorations for registration and for TEDA table

  - Candy for TEDA table

  - Pens and supplies for registration (scissors, tape, markers, pencils, extra pens, stapler...)

  - Confirm with DiaLog editor that she will be bringing extra copies of the DiaLog

  - Confirm that Administrative Assistant will bring membership renewal forms, some for TEDA table some to have with her during registration

  - Confirm that TEDA brochures have been printed and are ready for display at conference

  - Confirm that badges have been printed and are in alphabetical order and ready to put in the boxes for use at registration table

    - They need to include name and whether or not a member for the luncheon and gift)

  - Have the matrix printed for distribution at the conference (number of attendees plus 50)

  - If using a CEU documentation page, have it printed and ready

  - Finalize any plans for lunch on the second day, including board and speakers who requested lunch

Day prior to Conference

- You and the committee should be on site the day prior to the conference pretty early in the morning to prepare (if travel is involved you may want to arrive the night prior)

  - Check to be sure the materials you need to distribute at registration are ready

  - Collate the materials to be distributed

  - You may find it easier to have printed the on-site registration forms yourself and have them there as you prepare

  - Use the preparation room to prepare the gifts for distribution to members

  - Prepare list of who will do what at registration, usually done at board meeting

Conference Chair						3				October 2019

  - Prepare the registration and TEDA tables for the registration that begins the evening prior to the first day of the conference

    - Signs with letters of alphabet for sign in lines (enough chairs for those working registration to sit behind their assigned area)

    - Sign in sheets

    - Boxes for name badges, name badges in them and ready to go, and plastic badge holders

    - Pens for signing in

    - Materials to give to all attendees (matrix etc.…)

    - Gifts for members

    - Pens for all attendees?

    - Place for administrative assistant to set up her laptop and work on site registration

    - TEDA table: TEDA tablecloth, Membership forms, TEDA brochure, Dialogs, Candy and/or decorations, save the date flyer or postcard for next year

Conference Chair						4				October 2019

CONFERENCE GUIDANCE

(August 2016)

1. Organizational Considerations

2. Events/Meetings to be Included in Conference

3. Hotel/Conference Center Considerations

TEDA Conference

1. Organizational Considerations

Chairperson (s)

Treasurer: is the TEDA treasurer, the conference does not have a separate treasurer

Committees

Hotel/Conference Center: the conference chair person

  - Works closely with the hotel and signs the contract

  - Communicates needs for conference with hotel

  - Maintains communication with hotel to monitor number of rooms booked

  - Will work with hotel on food costs and commitments

  - During the conference will be the person to communicate needs with the

hotel/conference center as they arise

Speakers

  - Solicits speakers as per committee decisions

  - Obtains commitments in writing from speakers

  - Obtains speaker biographies, topics and other information for print/posting

  - Communicates with speakers in reference to their needs (hotel, food, travel,

audiovisual for conference, etc.) See speaker contract/confirmation

  - Obtain handouts from speakers

Registration

  - Is done by the TEDA administrative assistant

  - The committee/chair is responsible for obtaining the registration list(s), etc. from the TEDA administrative assistant

  - Brings printed lists of those registered to conference, including whether or not a TEDA member

  - Sets up the registration table with conference chair and has all materials needed for the registration table ready

  - Prepares onsite registration materials

  - Has receipt book to give receipts upon request

Vendors

  - Solicits vendors for conference

  - Obtains signed agreements from vendors

  - Collects fees from vendors

  - Provides vendor information to conference chair

  - Checks first day of conference to be sure tables are set up as desired

Publicity / Décor / Door Prizes

  - Creates “logo” based on conference them, uses it to help create and distribute flyers and registration forms in collaboration with the chair

  - Collaborates with chair to get flyers and forms to TEDA past president for distribution of flyer/registration electronically through members’ email and for posting on the TEDA website

  - Provides Dialog editor with electronic copy of flyer for DiaLog

  - Responsible for other means of promoting the conference

  - Responsible for the décor and general attractiveness of the conference

  - Is responsible for or works with a committee member to obtain door prizes if used

TEDA Conference

2. Events / Meetings To Be Included In Conference

Events/Meetings planned and paid for by the Committee

The conference itself:

- Rooms for keynote and breakout sessions

- Poster session and light reception (light finger foods, not a meal)

- If the annual General Session business meeting will be held at the conference, the conference chair is responsible for arranging for the room and meal.  (The president is responsible for planning and running the actual General Session)

Events/Meetings to be coordinated with TEDA board who is financially responsible

Day before the conference:

- TEDA executive board meeting (the conference chair is responsible for arranging for the room and accommodations requested by the president so that it is all one hotel/conference center contract).

TEDA Conference

3. Hotel/Conference Center Considerations (3 pages)

Negotiating the hotel/conference center is one of the more difficult aspects of the conference and is where the most problems will occur if not handled correctly.  It can cost thousands if the chair overcommits to dollar amounts and the conference is not well attended.

Conference Date:  The first decision is where and when the conference will be held.  It should be decided together (committee and/or board) as the preferred “when” may not be available at the preferred “where” and visa versa.  Multiple calls to venues to find options should begin years in advance of the conference, but due to our size and financial considerations, may be limited.  This will take time and patience, expect to spend some time negotiating.  You will need to be aware of what else is occurring at that same time of year, with particular attention to STAAR/ current state testing dates, religious holidays, school calendars/breaks (including school districts and universities), PEIMS reporting dates and the start and end of the year. When determining the location, consider factors such as easy access to airports/transportation, centrality to large pockets of TEDA members, and/or a destination that is desirable to diagnosticians (South Padre, Galveston, San Antonio have been successful). You should have a board approved four to eight-week block of time to work with.

Hotel/Conference Center Needs for Presentations/Sessions

- The committee needs to first determine the number of attendees you realistically expect

- Determine the schedule you would like to follow so you know the number of rooms you will need

  - Keynote?  If so when in the schedule

  - Breakout sessions?  Is so how many and when?  Will they repeat?

  - Other events/meetings as per list included

  - Will there be a reception /poster session/round table the first night and where will it be held?

- Look at room capacity for each of the sessions you will hold

  - Breakouts of 100 or 200 each? Room capacity smaller than 100 is not recommended.

  - Keynote of 400 -700?

  - We usually use classroom style seating (rows of chairs, no tables but that is the committee’s choice- although more expensive many prefer rows of tables which is classroom seating) for the sessions/presentations

  - If doing a poster session you need a large room and place to serve refreshments, or a hallway with room to serve.   How many do you plan to feed for the reception?

  - For general session:  how many do you expect to serve (TEDA members only) and what will the presentation be (buffet, sit down)?

- Plan meals for the full number of those attending the meal (general session is members only), but try not to overcommitted to a number (check with the last few years for a history of attendance)

  - See if you can commit to an overall dollar amount for food instead of a number of meals, that way you can change your meal plans to meet the dollar amount required by your contract (for example if you commit to a $10,000.00 food budget for the general assembly and reception and then find out you have fewer coming to the general assembly luncheon, you can either add to the reception, add a snack or food for the board meeting so that you use all the money allotted for food) You do not want to pay for meals you do not use.   DO NOT overestimate, most places will be happy to add, but will not subtract from what you committed to contractually.

  - Check the most recent conference numbers available to determine food amounts

  - Remember to keep the meal something neutral so most people will eat it. Buffets have been very well received recently because it is easier to offer more options and meet more dietary preferences.

  - You need to be careful when booking room size for meals, you want enough room for everyone to sit comfortably, but don’t want to over commit to food you have to pay for in case you don’t need that much.  Example: you are expecting and will feed 250 but want seating for 300 and food for 250.  (if serving buffet, hotels usually count the number of people they feed and bill you that)

- Always negotiate so that you are not paying for rooms for speakers, instead many venues will waive or comp the room rental because of your food budget.  Some venues do not do this as they do not cater (some conference centers) but their room rentals tend to be much less expensive and the food catered in is also less expensive so they balance out, but check into this before signing any contracts.

Hotel Considerations for Rooms (rooms for those spending the night)

- Hotel rooms that are convenient to location of sessions (either the same location, walking distance, or shuttle is provided if first two are not possible although they are a better option)

- Offers state rate – or rate very close

- Has enough rooms available that will be blocked for conference attendees

  - DO NOT OVERCOMMIT to rooms blocked for conference if you will be responsible for them (pay whether or not the rooms are booked/filled) Discuss adding later if necessary.

  - Get information from previous conference as to numbers of booked rooms for their conference – but remember to compare demographics

  - Reduce number of rooms needed if you are a metropolitan area where many will commute in for the day only and go home (resort areas, South Padre/San Antonio, will need more)

  - Negotiate attrition rate (how many rooms you committed to, but if unbooked, you do not

have to pay for them) 10% - 20% is usually reasonable.

  - Be sure there is a statement in the contract of them releasing rooms and you not paying for rooms booked by someone not associated with the TEDA conference when released.

  - Negotiate the cutoff date for people to book with TEDA at TEDA rates

  - Be sure that TEDA is not responsible for attendees who book and do not pay; it should read something like attendees booking rooms are responsible for their own charges.

Insurance

- TEDA carries liability insurance for all events including the conference – you may obtain a copy from the president or other board members

  - Insurance beyond what we have should not be needed.  Check these requirements before signing the contract (s).   Your committee may be financially responsible for additional insurance if it is required.

  - Insurance should not be needed for hotels that are sleeping rooms only.

Parking

- Parking is a must for both conference centers and the hotels

  - Preference is always free parking for attendees, but may not be available.  Be sure to note how parking will be handled in the registration form or flyers.

Shuttles

- Shuttles to and from convention centers that are not located within the hotel or within walking distance will be needed for attendees who do not have cars.

  - Be sure you agree with what the hotel considers walking distance, keeping in mind your attendees

  - Consider options if shuttles are not available – some form of transportation must be available.

- Shuttles between airports and hotels are not as common as in the past, especially in areas such as Galveston and San Antonio.  In recent years transportation to and from airports has been left up to the attendees.

Contracts

- Get copies of your contracts before signing them to allow for more than one committee chair or member to read and review before you sign it.

- KEEP A COPY OF YOUR CONTRACT once it has been signed by all parties.  You may need it if the hotel or conference center tries to change the terms, dates, or rates.

Tax Exempt Status

- TEDA is not tax exempt at this time.